## Sheet1
Planned Tasks/Activities | Weeks
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1.0 Business Underestanding
1.1 Research Project Title | bar: Weeks 0
1.2 Finalize Project Title & Supervisor | bar: Weeks 0
1.3 Understanding Business Domain | bar: Weeks 0 to Weeks 1
1.4 Milestone 1: Proposal | bar: Weeks 1
1.5 Submission of Finalized Proposal | bar: Weeks 1
2.0 Data Understanding
2.1 Identify Dataset | bar: Weeks 1 to Weeks 2
2.2 Discuss Proposal | bar: Weeks 2
2.3 Reevaluate Dataset | bar: Weeks 2 to Weeks 4
2.4 Write Draft Report | bar: Weeks 3 to Weeks 4
2.5 Milestone 2A: Oral Presentation | bar: Weeks 4
2.6 Present Current Findings & Progress | bar: Weeks 4
3.0 Data Preperation
3.1 Fine-Tune Draft Report based on Supervisor's & Examiner's Feedbacks | bar: Weeks 4 to Weeks 7
3.2 Clean & Filter Data | bar: Weeks 5 to Weeks 7
3.3 Examine Dataset Features | bar: Weeks 5 to Weeks 7
3.4 Split Data into Training & Testing Sets | bar: Weeks 5 to Weeks 7
3.5 Integrate the Datasets | bar: Weeks 5 to Weeks 7
3.6 Document Data Collection & Preperation into Draft Report | bar: Weeks 6 to Weeks 8
3.7 Write Executive Summary, Introduction & Preliminary Study | bar: Weeks 6 to Weeks 8
3.8 Milestone 2B: Draft Report | bar: Weeks 8
3.9 Submission of Draft Report | bar: Weeks 8
3.10 Fine-Tune Report based on Supervisor's and Examiner's Feedbacks | bar: Weeks 8 to Weeks 10
4.0 Modeling
4.1 Identification of Predictive Models | bar: Weeks 9 to Weeks 11
4.2 Apply Model Training Techniques | bar: Weeks 10 to Weeks 11
4.3 Assess Model's Accuracy & Performance | bar: Weeks 10 to Weeks 11
4.4 Analayze Patterns & Insights Generated | bar: Weeks 10 to Weeks 11
4.5 Model Comparison | bar: Weeks 11
4.6 Document Findings & Results in Report | bar: Weeks 11 to Weeks 13
4.7 Milestone 3A: Report | bar: Weeks 12 to Weeks 14
4.8 Submission of Complete Report to Supervisor & Examiner | bar: Weeks 12 to Weeks 14
4.9 Milestone 3B: Predictive Model Demo Showcase | bar: Weeks 15
4.10 Present Predictive Model to Examiners & Supervisor | bar: Weeks 15